## Sheet1
Unnamed:_0 | Unnamed:_1 | Unnamed:_2 | Unnamed:_3 | Unnamed:_4 | Unnamed:_5 | Unnamed:_6 | Unnamed:_7 | Unnamed:_8 | Unnamed:_9 | Unnamed:_10 | Unnamed:_11 | Unnamed:_12
| SR | Test Pack NO. | Item_Description | TP Total Weight [KG] | CONST. iN CHARGE | QC in Site | DATE COMPLETION | PUNC CLOSING | RFT | TEST DATE | Reinstatement | REMARKS
| 1 | K81-FPS4-P-01-TP-005-007 | HYDRO TEST | 124.53 | DHIRAJ |  | 45769 | 45769 | 45769 | 45770
| 2 | K90-OFF1-BD-01-TP-001-001 | HYDRO TEST | 13837.66 | DHIRAJ |  | 45930
| 3 | K90-OFF1-SR-01-TP-001-001 | HYDRO TEST | 9464.26 | DHIRAJ |  | 45922
| 4 | K81-FPS4-P-01-TP-004-001 | HYDRO TEST | 619.56 | DHIRAJ |  | 45919
| 5 | K81-FPS4-P-01-TP-006-006 | HYDRO TEST | 650.6 | DHIRAJ |  | 45915
| 6 | K81-FPS4-P-01-TP-003-001 | HYDRO TEST | 906.535 | DHIRAJ |  | 45914
| 7 | K90-OFF1-P-01-TP-001-001 | HYDRO TEST | 122.6533 | DHIRAJ |  | 45910
| 8 | K81-FPS4-P-01-TP-006-001 | HYDRO TEST | 13291.225 | DHIRAJ |  | 45910
| 9 | K90-OFF1-P-01-TP-0300-002 | HYDRO TEST | 0.2 | DHIRAJ |  | 45908
| 10 | K90-OFF1-P-06-TP-001-004 | HYDRO TEST | 513.855 | DHIRAJ |  | 45904
| 11 | K90-OFF1-P-07-TP-001-002 | HYDRO TEST | 189.12 | DHIRAJ |  | 45903 | 45903 | 45911
| 12 | K90-OFF1-P-01-TP-0300-001 | HYDRO TEST | 0.2 | DHIRAJ |  | 45902
| 13 | K90-OFF1-P-03-TP-0300-001 | HYDRO TEST | 84.8533 | DHIRAJ |  | 45902 |  | 45911
| 14 | K90-OFF1-P-07-TP-001-001 | HYDRO TEST | 8961.8 | DHIRAJ |  | 45901
| 15 | K90-OFF1-LPS-01-TP-001-006 | HYDRO TEST | 7838.03 | DHIRAJ |  | 45890
| 16 | K90-OFF1-LPS-01-TP-004 | HYDRO TEST | 7667.63 | DHIRAJ |  | 45887
| 17 | K90-OFF1-P-04-TP-001-001 | HYDRO TEST | 54798.68 | DHIRAJ |  | 45875 | 45893
| 18 | K90-OFF1-P-04-TP-0300-001 | HYDRO TEST | 7033.7167 | DHIRAJ |  | 45870
| 19 | K90-OFF1-RL-01-TP-001-002 | HYDRO TEST | 15596.3 | DHIRAJ |  | 45870 | 45873 | 45874 | 45874 |  | FOR PID REVIEW
| 20 | K81-IF-P-01-TP-003-002 | HYDRO TEST | 22774.06 | DHIRAJ |  | 45870 | 45872 | 45896
| 21 | K90-OFF1-P-03-TP-001-001 | HYDRO TEST | 6232.4383 | DHIRAJ |  | 45865
| 22 | K81-FPS4-P-01-TP-0300-001 | HYDRO TEST | 7426.365 | DHIRAJ |  | 45865
| 23 | K81-FPS4-P-01-TP-005-001 | HYDRO TEST | 135.87 | DHIRAJ |  | 45861
| 24 | K90-OFF1-P-07-TP-0300-001 | HYDRO TEST | 3.4 | DHIRAJ |  | 45861 | 45867
| 25 | K81-FPS2-BD-01-TP-001-003 | HYDRO TEST | 898.08 | DHIRAJ |  | 45860 | 45867 | 45868 | 45871
| 26 | K90-OFF-LPC-01-TP-003-001 | VISUAL TEST | 57.99 | DHIRAJ |  | 45858 | DONE
| 27 | K90-OFF-LPC-01-TP-002-011R | HYDRO TEST | 153.55 | DHIRAJ |  | 45858 | 45865 | 45867 | 45868
| 28 | K90-OFF1-P-04-TP-003-003 | VISUAL TEST | 86.1967 | DHIRAJ |  | 45854 | 45865
| 29 | K81-FPS4-P-01-TP-0300-002 | HYDRO TEST | 9179.64 | DHIRAJ |  | 45854
| 30 | K90-OFF-LPC-01-TP-002-010R | HYDRO TEST | 153.55 | DHIRAJ |  | 45849 | 45852 | 45854 | 45854
| 31 | K81-FPS2-P-01-TP-009-001 | HYDRO TEST | 131.155 | DHIRAJ |  | 45848 | 45893 |  |  |  | FOR PID REVIEW
| 32 | K90-OFF-LPC-01-TP-001-003 | HYDRO TEST | 1487.21 | DHIRAJ |  | 45848 | 45852 | 45855 | 45855
| 33 | K81-FPS1-BD-01-TP-001-003 | HYDRO TEST | 1005.285 | DHIRAJ |  | 45848 | 45871 | 45872 | 45874
| 34 | K90-OFF1-IA-01-TP-001-001 | SERVICE TEST | 2194.8 | DHIRAJ |  | 45847
| 35 | K90-OFF1-IA-01-TP-002-001 | SERVICE TEST | 2166.14 | DHIRAJ |  | 45847 | 45849
| 36 | K90-OFF-LPC-01-TP-001-004 | HYDRO TEST | 18 | DHIRAJ |  | 45845
| 37 | K90-OFF1-LPC-01-TP-001-004 | HYDRO TEST | 3428.23 | DHIRAJ |  | 45845 | 45869 | 45879 | 45911
| 38 | K90-OFF-LPC-01-TP-001-006 | HYDRO TEST | 1487.21 | DHIRAJ |  | 45838 | 45853 | 45854 | 45854
| 39 | K90-OFF-LPC-01-TP-002-002 | HYDRO TEST | 2558.61 | DHIRAJ |  | 45836 | 45837 | 45838 | 45838
| 40 | K90-OFF-LPC-01-TP-002-010 | HYDRO TEST | 153.55 | DHIRAJ |  | 45836 | 45843 | 45843 | 45844
| 41 | K81-FPS1-P-01-TP-0300-001 | HYDRO TEST | 8255.12 | DHIRAJ |  | 45834 | 45838 | 45839 | 45839
| 42 | K81-FPS2-P-01-TP-0300-002 | HYDRO TEST | 8211.04 | DHIRAJ |  | 45834 | 45839 | 45839 | 45839
| 43 | K81-FPS2-P-01-TP-005-003 | HYDRO TEST | 8211.04 | DHIRAJ |  | 45834 | 45874 | 45879 | 45886
| 44 | K81-FPS2-P-01-TP-005-002 | HYDRO TEST | 8211.04 | DHIRAJ |  | 45834 | 45875 | 45885 | 45886
| 45 | K81-FPS1-P-01-TP-003-003 | HYDRO TEST | 0.8 | DHIRAJ |  | 45834 |  | 45907 | 45907
| 46 | K81-FPS2-P-01-TP-003-002 | HYDRO TEST | 92.79 | DHIRAJ |  | 45832 | 45498 | 45904 | 45906
| 47 | K81-FPS4-BD-01-TP-001-001 | HYDRO TEST | 135.56 | DHIRAJ |  | 45830 | 45900
| 48 | K90-OFF-LPC-01-TP-002-007 | HYDRO TEST | 372.47 | DHIRAJ |  | 45828 | 45858 | 45860 | 45861
| 49 | K90-OFF-LPC-01-TP-002-011 | HYDRO TEST | 153.55 | DHIRAJ |  | 45826 | 45831 | 45832 | 45832
| 50 | K81-IF-P-01-TP-003-001 | HYDRO TEST | 45548.12 | DHIRAJ |  | 45825 | 45868
| 51 | K90-OFF-LPC-01-TP-002-009 | HYDRO TEST | 153.55 | DHIRAJ |  | 45823 | 45827 | 45827 | 45827
| 52 | K90-OFF1-P-01-TP-001-005 | HYDRO TEST | 135 | DHIRAJ |  | 45822 | 45823 | 45824 | 45824
| 53 | K90-OFF1-LPC-01-TP-003 | HYDRO TEST | 3385.48 | DHIRAJ |  | 45822 | 45878 | 45880 | 45911
| 54 | K90-OFF1-P-01-TP-002-002 | HYDRO TEST | 4244.65 | DHIRAJ |  | 45818 | 45827 | 45832 | 45833
| 55 | K90-OFF1-OWS-01-TP-003-001 | HYDRO TEST | 2176.07 | DHIRAJ |  | 45816 | 45821 | 45823 | 45823
| 56 | K81-FPS4-P-01-TP-003-007 | HYDRO TEST | 240.2 | DHIRAJ |  | 45815 | 45818 | 45818 | 45818
| 57 | K81-FPS2-P-01-TP-008-001 | HYDRO TEST | 116.955 | DHIRAJ |  | 45813 | 45815 | 45815 | 45815
| 58 | K90-OFF1-P-02-TP-001-001 | HYDRO TEST | 7885.72 | DHIRAJ |  | 45806 | 45809 | 45811 | 45811
| 59 | K81-FPS2-BD-01-TP-001-001 | HYDRO TEST | 1170.17 | DHIRAJ |  | 45806 | 45818 | 45818 | 45819
| 60 | K90-OFF1-P-05-TP-001-001 | HYDRO TEST | 10574.31 | DHIRAJ |  | 45805 | 45815 | 45815 | 45817
| 61 | K81-FPS4-P-01-TP-006-005 | HYDRO TEST | 67.4 | DHIRAJ |  | 45802 | 45804 | 45804 | 45805
| 62 | K90-OFF1-P-04-TP-002-001 | HYDRO TEST | 124.88 | DHIRAJ |  | 45800 | 45801 | 45801 | 45802
| 63 | K81-FPS2-P-01-TP-006-001 | HYDRO TEST | 120.78 | DHIRAJ |  | 45800 | 45801 | 45802 | 45802
| 64 | K90-OFF1-P-03-TP-001-003 | HYDRO TEST | 84.8533 | DHIRAJ |  | 45798 | 45800 | 45800 | 45800
| 65 | K81-FPS4-P-01-TP-005-002 | HYDRO TEST | 130.43 | DHIRAJ |  | 45796 | 45798 | 45799 | 45799
| 66 | K81-FPS4-P-01-TP-005-006 | HYDRO TEST | 131.63 | DHIRAJ |  | 45796 | 45798 | 45799 | 45799
| 67 | K81-FPS2-P-01-TP-005-004 | HYDRO TEST | 239 | DHIRAJ |  | 45788 | 45790 | 45790 | 45790
| 68 | K90-OFF1-SR-01-TP-001-003 | HYDRO TEST | 789 | DHIRAJ |  | 45788 | 45808 | 45810 | 45810
| 69 | K90-OFF1-P-05-TP-001-004 | HYDRO TEST | 34.7 | DHIRAJ |  | 45785 | 45785 | 45786 | 45786
| 70 | K81-FPS1-P-01-TP-010-001 | HYDRO TEST | 131.53 | DHIRAJ |  | 45785 | 45788 | 45788 | 45788
| 71 | K81-FPS2-P-01-TP-010-001 | HYDRO TEST | 134.23 | DHIRAJ |  | 45785 | 45788 | 45788 | 45788
| 72 | K90-OFF1-P-08-TP-001-004 | HYDRO TEST | 16364.2 | DHIRAJ |  | 45752 | 45753 | 45753 | 45754
| 73 | K81-FPS1-BD-01-TP-001-001 | HYDRO TEST | 1208.125 | DHIRAJ |  | 45743 | 45756 | 45757 | 45758
| 74 | K90-OFF1-P-07-TP-001-005 | HYDRO TEST | 8961.8 | DHIRAJ |  | 45724 | 45729 | 45729 | 45730
| 75 | K90-OFF1-P-01-TP-002-001 | HYDRO TEST | 4244.65 | DHIRAJ |  | 45719 | 45729 | 45729 | 45729
| 76 | K81-FPS2-P-01-TP-0300-001 | HYDRO TEST | 777.63 | DHIRAJ |  | 45605 | 45616 | 45619 | 45778
| 77 | K90-OFF1-P-04-TP-004-001 | HYDRO TEST | 117.03 | DHIRAJ |  | 45566 | 45567 | 45568 | 45568
| 78 | K81-FPS2-P-01-TP-007-001 | HYDRO TEST | 140.905 | DHIRAJ |  | 45564 | 45573 | 45573 | 45585
| 79 | K81-IF-P-01-TP-002-001 | HYDRO TEST | 150.25 | DHIRAJ |  | 45546 | 45551 | 45551 | 45551
| 80 | K81-FPS2-P-01-TP-003-001 | HYDRO TEST | 53.89 | DHIRAJ |  | 45540 | 45575 | 45613 | 45776
| 81 | K90-OFF1-P-04-TP-005-001 | HYDRO TEST | 123.05 | DHIRAJ |  | 45524 | 45528 | 45529 | 45532
| 82 | K81-FPS1-P-01-TP-007-001 | HYDRO TEST | 116.205 | DHIRAJ |  | 45518 | 45524 | 45525 | 45539
| 83 | K81-FPS2-P-01-TP-011-001 | HYDRO TEST | 133.605 | DHIRAJ |  | 45518 | 45524 | 45525 | 45539
| 84 | K90-OFF1-P-04-TP-003-001 | HYDRO TEST | 86.1967 | DHIRAJ |  | 45495 | 45864 | 45866 | 45866
| 85 | K81-FPS1-P-01-TP-008-001 | HYDRO TEST | 135.52 | DHIRAJ |  | 45469 | 45512 | 45514 | 45530
| 86 | K90-OFF-LPC-01-TP-002-001 | HYDRO TEST | 51.84 | DHIRAJ |  | 45431 | 45492 | 45493 | 45493